## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
BMD | 2241-swen-261-8-c BMD
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | AD; 11/06/2024 | Pass | AD; 11/10/2024
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | AD; 11/06/2024 | Pass | AD; 11/10/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see each need. | Pass | AD; 11/06/2024 | Pass | AD; 11/10/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | AD; 11/06/2024 | Pass | AD; 11/10/2024
As a Helper, I want to update my account information so it remains up to date | GIVEN I submit a request to update a certain aspect of my profile WHEN I need to update current information THEN the server will update my personal info and return 200 OK | Pass | CD; 11/06/24 | Pass | CD; 11/10/24
As a User I want to login to the system so that I am provided with the proper permissions when I interact with the system. | GIVEN I have entered my username before WHEN I sign in using the same username using the UI THEN I expect to have access to the same basket and wishlist. | Pass | BK, 11/06/24 | Pass | BK, 11/010/24
| GIVEN I have not accessed the service before WHEN I try to access the service THEN I am prompted to create an account. | Pass | BK, 11/06/24 | Pass | BK, 11/10/24
As a User I want to be able to interact with the data via the web UI so that I can effectively use the service. | GIVEN I am interacting with a fully running stack WHEN I change data using the UI THEN I expect those changes to be reflected in the database | Pass | OT; 11/06/24 | Pass | OT; 11/10/24
As a Helper I want to pay for all the needs in my basket at once so that the process of contributing to needs is simplified. | GIVEN A user requests a to checkout their basket WHEN they submit the request to do so THEN their basket will be cleared and 200 OK will be returned | Pass | CD; 11/06/24 | Pass | CD; 11/10/24
As a User I want to be able to either sign into a current user or sign up as a new user. | GIVEN I am not signed in as a user WHEN I go to the sign in page I can THEN either enter a username into sign in to sign in or sign up and add a new user. | Pass | FG; 11/6/2024 | Pass | FG; 11/10/2024
As a User I want to be able to see all of the needs available to select from to put into the needs basket. | GIVEN I am signed in as a user WHEN I go to the needs tab THEN I expect to see all the needs available to purchase. | Pass | FG; 11/6/2024 | Pass | FG; 11/10/2024
As a User I want to be able to interact with the tabs in the navigation bar to move to the different web pages. | GIVEN I am on the site I can see the navigation bar at all times WHEN I the tabs in the navigation bar THEN I expect to go to the correlated page of the tab. | Pass | CD; 11/6/2024 | Pass | CD; 11/10/24
As a User I want to be able to interact with the profile via the profile tab so that I can see my username and user id. | GIVEN I am signed in as a user WHEN I click on the profile tab in the navigation bar THEN I expect to see my username and user id | Pass | OT; 11/06/24 | Pass | OT; 11/10/24
As a User I want to be able to go to the dashboard/home page to see the home of the site. | GIVEN I am either logged in or no WHEN I go to the dashboard THEN I expect to see the home page of the site | Pass | BK, 11/06/24 | Pass | BK, 11/10/24
As a Helper I want to add or remove needs from my basket so that I can have all the needs that I want to immediately contribute to in one place | GIVEN I submit a request to add a given need to my basket WHEN that need exists THEN the system will add the need to the basket and return a 200 OK. | Pass | CD; 11/06/24 | Pass | CD; 11/10/24
| GIVEN I submit a request to add a given need to my basket WHEN that need does not exists THEN the system will not add the need to the basket and return a 200 OK | Pass | CD; 11/06/24 | Pass | CD; 11/10/24
As a Helper I want to pay for all the needs in my basket at once so that the process of contributing to needs is simplified | GIVEN I have a full funding basket as a Helper WHEN I check out, THEN the basket is emptied and the needs cupboard is updated accordingly. | Pass | OT; 11/06/24 | Pass | OT; 11/10/24
As a Helper I want to transfer needs from my wish list to my basket to check-out when I am ready to contribute to them. | GIVEN a user wants to transfer needs to their wish list WHEN a request to do so is submitted THEN the system will return 200 OK and transfer the need | Pass | CD; 11/06/24 | Pass | CD; 11/10/24
As a Helper I want to transfer needs from my wishlist to the funding basket so they can be checked out | GIVEN a user submists a request to transfer a need from a basket WHEN that need is avalible THEN the systmem will do so and return 200 OK |  |  | Pass | CD, 11/06/2024
| GIVEN a user submists a request to transfer a need from a basket WHEN that need is NOT avalible THEN the systmem return NOT_FOUND |  |  | Pass | CD, 11/06/2024
As a Helper I want to add/remove needs to a wish list, so that I can easily find them later when I am ready to purchase them. | GIVEN a user submits a request to add a need WHEN that need is avalible in the cupboard THEN the need will be added and 200OK will be returned. |  |  | Pass | CD, 11/06/2024
| GIVEN a user submits a request to add a need WHEN that need is NOT avalible in the cupboard THEN NOT_FOUNDwill be returned. |  |  | Pass | CD, 11/06/2024
| GIVEN a user submits a request to remove a need WHEN that need is NOT avalible in the wishlist THEN NOT_FOUND will be returned. |  |  | Pass | CD, 11/06/2024
| GIVEN a user submits a request to remove a need WHEN that need is avalible in the wishlist THEN the need will be removed and return 200OK |  |  | Pass | CD, 11/06/2024
As a user I want an intuitive ad easy to follow UI for my wishlist so I may add needs easily to and from the basket as well as transfer them to my funding bacsket | GIVEN a user presses a button to add a need from the cubboard to their wishlist WHEN there is quantity avalible THEN the need will showup in their wishlist UI |  |  | Pass | CD, 11/06/2024
| GIVEN a user presses a button to add a need from the cubboard to their wishlist WHEN there is NOT quantity avalible THEN the need will NOT showup in their wishlist UI |  |  | Pass | CD, 11/06/2024
| GIVEN a user presses a button to remove a need from their wishlist WHEN thery want to do so THEN the need will be removed |  |  | Pass | CD, 11/06/2024
| GIVEN a user presses a button to transfer a need from their wishlist to thheir funding basket WHEN thery want to do so THEN the need will be transferd in the UI |  |  | Pass | CD, 11/06/2024
As a Helper I want to add needs to a wish list, so that I can easily find them later when I am ready to purchase them. | Given a user presses the checkout button when the user's funding basket is not empty then the funding basket will be emptied and the user checked out |  |  | Pass | AD, 11/10/2024
As a Helper I want and intuitive and easy to follow design for my subscribed needs, showing the renewal date and other such related things so that I can stay informed regarding when my next payment will come due | GIVEN i click a button to add a need to my subscription list WHEN it is avalible in the cupboard THEN it will be added in teh UI |  |  | Pass | FG, 11/10/2024
| GIVEN I click a button to remove a subscription WHEN it is in my sub list THEN the subscription will be removed from the UI |  |  | Pass | FG, 11/10/2024
As a Helper I want to add or remove needs to my subriptions list so i can continously suport them on a period basis | GIVEN i submit a request to add a given need to my subscription list WHEN that need exists THEN the system will add the need to the supcription list and return a 200 OK |  |  | Pass | OT, 11/10/2024
| GIVEN i submit a request to add a given need to my subscription listWHEN that need does not exists THEN the system will not add the need to the subscription list and return a 200 OK |  |  | Pass | OT, 11/10/2024